ASTON-CUM-AUGHTON PARISH COUNCIL

ACTION PLAN

2021 – 2023

This Action Plan summaries the projects and proposals that Aston-cum-Aughton Parish Council, occasionally in partnership with others, will develop and/or deliver during a 3 year term commencing 2021. From time to time the document will be subject to alteration and amendment and will inform the budget setting process.

Partners

Amongst others these include: Rotherham Borough Council, South Yorkshire Police, Sheffield City Council.

Review and Evaluation

The Action Plan will be formally reviewed every 6 months. It is a ‘live’ document that the Council can add to and amend as necessary. Progress on projects will be reviewed by Members of Aston-cum-Aughton Parish Council.

Key: APC – Aston-cum-Aughton Parish Council

CURRENT & FUTURE PROJECTS

| No | Description | Key Tasks | Responsibility | Timescale | Update |
| --- | --- | --- | --- | --- | --- |
| APC1 | Investments | - 4 x Investments to be opened | Full Council | June 23 | Investments have been applied for, 3 of which are now open. |
| APC2 | Climate Emergency Plan | - That the Council establishes a Climate Emergency Plan for the Parish - Contact RMBC for their plan - Speak to user groups and football teams - Purchase tablets for Councillors - Arrange a meeting with new Climate Officer at RMBC | Full Council - delegated to the General Purpose Committee, recommendations ratified at Full Council | August 2021 April 2023 | Tablets purchased August 2021 |
| APC3 | Lodge Lane Football Pitch | - Move the football pitch 10m in from its current position - Re-seed the goal mouths | Full Council – delegated to the Recreation & Open Spaces Committee, recommendations ratified at Full Council |  | Work completed to an unsatisfactory standard. Additional work completed by RMBC September ‘21 Pitch playable for 2022 season New goal posts purchased August ‘22 |
| APC4 | Traffic calming – Fair View Drive | - Consult with residents, ask for their suggestions - Costings for a new bollard - Signage | Full Council – delegated to Recreation & Open Spaces Committee, recommendations ratified at Full Council |  | Bollards fitted September ‘21 |
| APC5 | Governance | - Ensure policies/procedures are up to date and brought to Full Council | Clerk Full Council | Ongoing |  |
| APC6 | Aston-cum-Aughton Parish Council Emergency Plan | - Finalise the Emergency Plan document - Consult key partners - Recruit volunteers - Promote the completed plan to residents and key partners | Full Council – delegate to the General Purpose Committee RMBC | Sept ‘23 |  |
| APC7 | Notice Boards | - Refurbishment of noticeboards - Ensure information is uniformed on all boards | Full Council | Ongoing | The Chase & Reading Rooms noticeboards renewed Dec 2021 Lineal park noticeboard renewed June 2022 Wetherby noticeboard renewed March ‘23 |
| APC8 | Website | - To complete work on the new website ready for it going live - Ensure all documents are accessible documents - Website kept up to date | APC | New Website August 2021 Ongoing | Website compliant with accessibility and transparency. Website live December 2021 – work will be ongoing |
| APC9 | Skate Park, MUGA, Fitness Equipment, Play area and CCTV for Burgoyne Park Phase 1 of Recreation facilities improvements | - To look into funding for a skate park, MUGA, fitness equipment and play equipment - To write a tender document for a skate park - To consult with residents - To source companies for a skate park and obtain references | Full Council – delegated to the Recreation & Open Spaces Committee, recommendations ratified at Full Council | MUGA & Skatepark to be completed for September 2023 | Funding sourced, consultation information on survey monkey and has gone out to a resident and Simon Dungworth Quotes for the MUGA, play area and fitness area received Consultation taken to schools and at the annual Gala on Lodge Lane Survey completed – funding applied for March 2022 Funding successful 10 June 2022 £100k Skatepark tender on Contracts Finder ‘22 Skatepark design & quote received New MUGA design & quote received Company advised they had the contract for the Skatepark & MUGA March 2023 Fitness equipment removed March ‘23 new safety surface for the swings installed March ‘23 MUGA completed July ‘23 Skatepark to commence July ‘23 |
| APC10 | Quality Award under the Local Council Award Scheme | - To start working towards the Foundation status under Local Council Award Scheme | Full Council | Ongoing | Clerk attending a training course in 23rd June 2022 |
| APC11 | Open Space – Lodge Lane, Leonard Kyte, Fence, Old Aughton Rec, Bowling Greens | - To ensure all play equipment is in working order and any advisory work from the inspection reports is completed - To gain quotes for CCTV at Lodge Lane, Leonard Kyte and Burgoyne Park - To ensure the grounds maintenance work completed by RMBC is to a good standard - New roof on Lodge Lane Changing Rooms - New electrics and lighting in Lodge Lane Changing Rooms - Showers to be checked and fixed at Lenard Kyte Changing Rooms - Legionnaire check - Playarea at Lodge Lane - Removal of shrubs etc from bottom of Lodge Lane near to Southlands To keep looking for funding available for all sites | APC – delegated to Recreation and Open Spaces Committee Clerk Clerk | Ongoing Ongoing Ongoing | Completed November 2021 Completed December 2021 Completed January 2022 Working with Legionella company with regard to testing and becoming compliant Funding applied January ’23 – unsuccessful March ‘23 Work carried out on the Lodge Lane site March ‘23 |
| APC12 | Allotments | - To ensure all plots are let and part cultivated - To produce new policies for the keeping of livestock on the allotments - To set the fees and charges | APC – delegated to Recreation and Open Spaces Committee | Ongoing | Quarterly checks undertaken by the Clerk, new plots have been allocated Requires a visit urgently 13.06.22 4 Allotment holders evicted new plot created, all plots now let March ‘23 |
| APC13 | Aston and Swallownest Cemetery | - To ensure all legal requirements are undertaken - To ensure 5 yearly monument testing is undertaken - To review the opening and closing times of the cemetery - To set the fees and charges for the cemeteries - To implement new rules and regulations for the cemeteries - Clearing of vegetation from Aston cemetery - New fence at Aston Cemetery - Water system changed to tap - Stone work on Worksop Road re-pointed - Gates at Aston Cemetery cleaned and repainted - Railings/gates at Swallownest Cemetery cleaned and repaired - Christmas Trees for Cemeteries | Full Council – delegated to General Purpose Committee | Monument testing March ‘23 Ongoing | Cemeteries system for transfer of grave ownership updated and distributed to funeral directors New cemeteries database purchased and in place, old burial records being inputted – Swallownest fully inputted Dec ‘22 New rules and regulations and policies in place. Installed January ‘23 Completed September ‘22 Tap completed summer ‘22 Lime tree felled other pruned ‘Feb 23 Gates at Aston repainted ‘23 Pointing on the Arch and wall completed March ‘23 |
| APC14 | Newsletter (Parish Natter) | - To form a working group to write the Parish Natter - To contact companies re new format of the newsletter | Clerk and working group | To be completed by 30 Sept ‘23 |  |
| APC15 | Social Media | - To establish a Clerk & Council Facebook public page - To write a social media policy to be adopted by Council | Clerk |  | Clerk & Aston-cum-Aughton Parish Council pages set up and live Adopted |
| APC16 | Council Surgery | - To set up a Parish Council Surgery once a month | Clerk and APC Councillors |  |  |
| APC17 | Cleaner Parish | - To establish monthly community litter picks - To purchase litter picking equipment | Full Council - delegate to Recreation and Open Spaces Committee | Ongoing | First litter pick January 2022 Equipment purchased October 2021 |
| APC18 | Events | - To hold a Bonfire/firework event in November - To have Christmas lights within the Parish - Queens Platinum Jubilee - Kings Coronation | APC – delegated to Recreation & Open Spaces Committee | November December June | Bonfire went ahead Lights and Cribs installed 2021 Beacon lighting & picnic in the park agreed and went ahead but at Parish Hall Kings Coronation street party donation |
| APC20 | Parish Hall | - To manage the Parish Hall on behalf of the Management Committee - To upkeep the Parish Hall (see separate work sheet) - To ensure Health & Safety is up to date - To update the noticeboards - Governance work to be updated including trustees and uploading to Charity Commission | APC Parish Hall Management Committee | May ‘23 | Completed December 2021 |
| APC21 | Winter/Summer Planting | - To ensure that the Parish is planted throughout the year to a high standard |  |  | Summer Planting booked for 2022 Spring bedding booked for ‘22/’23 Summer bedding booked for ‘23/24 |
| APC22 | Reading Room | - To gain quotes to re-render the reading room - Look into funding for the rendering work - Look into the heating system | Full Council Full Council | Dec ‘23 | One quote received Heritage Lottery and Historic England have both refused to fund Quotes received July 2022 New 3 quotes received February ‘22 Bring back to Council April ‘23 Company awarded work May ’23 – work to commence May ‘24 |
| APC23 | Clearance of land at King Street | - Quotes for land clearance - Land valued for asset register - Surveyor to value land | APC - Clerk |  | Awaiting quotes from 2 companies June ‘22 Land cleared September ‘22 Awaiting surveyor March ‘23 |
| APC24 | Pathway adjacent to Aughton Early Years | - Trench to be dug with landscaping | APC - Clerk |  | Awaiting quotes June ‘22 Work completed August ‘22 |
| APC25 | Swallownest Cemetery – Extension | - Planning permission to be applied for, change of use of land - Cemetery extension requires mapping out of graves and road layout - Bio diversity plan needs undertaking - Standing water plan needs to be checked | APC delegated to General Purpose Committee Clerk |  | Quotes to be sourced September ‘23 Discussion with RMBC planning May ‘23 Discussion with Environment Agency |
| APC26 | Old Aughton Recreation Ground Phase 2 Recreation Facilities Improvements | - Landscape design on Old Aughton Rec - Source Funding | APC delegated to Recreation & Open Spaces Committee |  | Meeting with RMBC Landscape Team April ‘23 Landscape Team awarded work June 2023 |
| APC27 | Christmas Lights & Event | - Quotes for Christmas Light - Contact with RMBC re feeder pillar for a Christmas tree - Event for Christmas Lights | APC delegated to Recreation & Open Spaces |  | Quotes received March ‘23 Meeting April ‘23 Quotes from RMBC not received |
| APC28 | Tree – Heron Hill | - Residents to be contacted - Quotes from Tree surgeons - Road Closure | APC - Clerk |  | Tree removed March ‘23 |